## INVOICE
BILL OF SUPPLY
AMIT KUMAR SINGH
PLOT.NO - 5, KADIPUR
SEC-10, GURGAON (HR) 122001
PAN-IWZPS5026P
Bill to - TREHAN HOSPITALITY & REALITY PVT LTD. | Place of Supply |  |  | INVOICE No | Dated
ADD - GF, 641 P, SEC-38 GURUGRAM,122001
HARYANA
|  |  |  | RA/JUNE/02 | 2023-06-10
Description of Services | SAC | QTY | Units | RATE | Amount
ELECTRICAL WORK |  |  |  |  | 54222
Total |  |  |  |  | 54222
Taxable Value |  |  |  |  | 54222
Total Payable
Total |  |  |  |  | 54222
Amount Chargeable (in words)
Rupees only
AMIT KUMAR SINGH
Authorised Signatory

## COP
Certificate of Payment
AMIT KUMAR SINGH
Name of Project :- |  | Adani Plots |  |  | Date of Start : N/A
Location :- |  | Gurgaon |  |  | Date of Completion : N/A
Name of Agency :- |  | AMIT KUMAR SINGH |  |  | Contract Value : N/A
Bill Number & Bill Date :- |  | Monthly Bill (01-01-2023) |  |  | Contact Value : 7503025872
Bill Period :- |  | 26-11-2022 TO 25-12-2022
Nature of Work :- |  | ELECTRICAL WORK
PAN Number :- |  | IWZPS5026P
GST Number :- |  | N/A
Monthly Bill (26 NOV 2022 to 25 DEC 2022)
S.No. | Description |  |  | Amount Upto Last Bill | Amount Upto Date | Amount for this Bill | Remarks
A | PAYMENT DETAIL
1 | Value of work done
| a | Total of Work Done |  | 20055.75 | 41865.45 | 21809.7
| b | Total of Labour Supply |  | 0 | 0 | 0
|  | Total (A0) |  | 20055.75 | 41865.45 | 21809.7
2 | Add Taxes
| a | CGST @9% on (A0) |  | 0 | 0 | 0
| b | SGST @9% on (A0) |  | 0 | 0 | 0
| c | IGST @18% on (A0) |  | 0 | 0 | 0
|  | Sub Total of Taxes (A1) |  | 0 | 0 | 0
| Total value of Work done & Taxes (A) = (A0+A1) |  |  | 20055.75 | 41865.45 | 21809.7
B | DEDUCTIONS
| B-1 | Retention Money @ 10% on (A0) |  | 2005.575 | 4186.545 | 2180.97
| B-2 | TDS @ 1% on (A0) |  | 200.5575 | 418.6545 | 218.097
| B-3 | Mobilization Amount |  | 0 | 0 | 0
|  | Total (B) |  | 2206.1325 | 4605.1995 | 2399.067
C | Net Payable Amount (A-B) |  |  | 17849.6175 | 37260.2505 | 19410.633
D | DEDUCTIONS & RECOVERIES
| D-1 | Less Ad-hoc / Kharcha |  | 0 | 11286 | 11286
| D-1 | Payment |  | 0 | 0 | 0
| D-2 | Less Debits for labour supply if any |  | 0 | 0 | 0
| D-3 | Less for Material Supply |  | 0 | 0 | 0
| D-4 | Less for Electricity if any |  | 0 | 0 | 0
| D-5 | Hold for Housekeeping |  | 0 | 0 | 0
| Total Deductions & Recoveries (D) |  |  | 0 | 11286 | 11286
E | Total Final Part payable Amount (Rounding Off) (C-D) |  |  | 17849.6175 | 25974.2505 | 8124.633
Amount In Words :- EIGHT THOUSAND ONE HUNDRED TWENTY FIVE ONLY.
Note:-
This is full and final payment of above mentioned billing period.
you are agreed that you will not consider and claim any other payment apart from this COP final payable amount.
You are agreed that company will not liable to pay any money of your labour and all the your worker payment will be done by you and company is not liable for the same.
You agree that all debits for material supply and labour deployed at your risk and cost are in your knowledge and are being deducted as per material details attached or as per Daily labour report.
Name, Signature & Date |  |  | Name, Signature & Date | Name, Signature & Date |  | Name, Signature & Date
Contractor |  |  | Billing HOD & Manager Billing | Executive Director |  | MD
AMIT KUMAR SINGH |  |  | Mr. Pradeep Singh & Mr. Shashank | Mr. Inder Kamra |  | Mr. Nisarg Trehan / Mr. Archit Budhia
Beneficiary Name : |  |  | AMIT KUMAR SINGH
Beneficiary Account Number : |  |  | 20419791497
IFSC CODE : |  |  | SBIN0007046

## ABSTRACT
ABSTRACT
Name Of Agency:- |  | M/S. AMIT KUMAR SINGH
Bill Period |  | 26-11-2022 TO 25-12-2022
Nature of Work :- |  | ELECTRICAL WORK
WORK DONE
S.No. | Site Details | Previous Bill Amount | This Bill Amount | Upto this Bill Amount | TDS @ 1% | Hold Retention Money @ 10% | Payable | Net Payable Previous | KHARCHA | Balance Payment | Remarks
1 | J-41 | 6329.4 | 12658.8 | 18988.2 | 189.882 | 1898.82 | 16899.498 | 5633.166 | 11286 | -19.668
2 | J-42 | 13726.35 | 9150.9 | 22877.25 | 228.7725 | 2287.725 | 20360.7525 | 12216.4515 |  | 8144.301
| Total | 20055.75 | 21809.7 | 41865.45 | 418.6545 | 4186.545 | 37260.2505 | 17849.6175 | 11286 | 8124.633
LABOUR SUPPLY
S.No. | Site Details | Previous Bill Amount | This Bill Amount | Upto this Bill Amount | TDS @ 1% | Hold Retention Money @ 10% | Payable | Net Payable Previous | KHARCHA | Balance Payment | Remarks
1 | J-41 |  | 0 | 0 | 0 |  | 0 |  |  | 0 | SUPPLY
|  |  | 0 |  | 0 |  | 0 |  |  | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total A+B |  | 20055.75 | 21809.7 | 41865.45 | 418.6545 | 4186.545 | 37260.2505 | 17849.6175 | 11286 | 8124.633

## DEBIT
SUMIT SINGH ELECTRICAL
DEBIT DETAILS
S.NO. | DATE | DESCRIPTION |  |  | AMOUNT
1 | 2022-08-10
2 | 2022-09-10
3 | 2022-10-10
4
5 |  |  |  |  | 0
6 |  |  |  |  | 0
A |  | ALL TOTAL | 0 | 0 | 0 | 0

## J-41
PLOT NO. J-41, ADANI
AMIT KUMAR SINGH CONTRACTOR
S.NO. | DESCRIPTION | UNIT | QTY. | AREA | RATE | AMOUNT | STATUS
1 | STILT FLOOR | SQFT. | 0.15 | 3836 | 11 | 6329.4 | SLAB COND.(15%)
2 | FIRST FLOOR | SQFT. | 0.15 | 3836 | 22 | 12658.8 | SLAB COND.(15%)
3 | SECOND FLOOR | SQFT. |  | 3836 | 22 | 0
4 | THIRD FLOOR | SQFT. |  | 3836 | 22 | 0
5 | FOURTH FLOOR | SQFT. |  | 3836 | 22 | 0
6 | TERRACE FLOOR | SQFT. |  | 3836 | 11 | 0
| SUB TOTAL |  |  |  |  | 18988.2
SUPPLY
| MASON | NOS. |  |  | 650 | 0
| LABOUR | NOS. |  |  | 450 | 0
DEBIT
| MASON | NOS. |  |  | 650 | 0
| HELPER | NOS. |  |  | 450 | 0
| SUB TOTAL |  |  |  |  | 0

## J-42
PLOT NO. J-42, ADANI
AMIT KUMAR SINGH CONTRACTOR
S.NO. | DESCRIPTION | UNIT | QTY. | AREA | RATE | AMOUNT | STATUS
1 | STILT FLOOR | SQFT. | 0.15 | 2773 | 11 | 4575.45 | SLAB COND.(15%)
2 | FIRST FLOOR | SQFT. | 0.15 | 2773 | 22 | 9150.9 | SLAB COND.(15%)
3 | SECOND FLOOR | SQFT. | 0.15 | 2773 | 22 | 9150.9 | SLAB COND.(15%)
4 | THIRD FLOOR | SQFT. |  | 2773 | 22 | 0
5 | FOURTH FLOOR | SQFT. |  | 2773 | 22 | 0
6 | TERRACE FLOOR | SQFT. |  | 2773 | 11 | 0
| SUB TOTAL |  |  |  |  | 22877.25
SUPPLY
| MASON | NOS. |  |  | 650 | 0
| LABOUR | NOS. |  |  | 450 | 0
DEBIT
| MASON | NOS. |  |  | 650 | 0
| HELPER | NOS. |  |  | 450 | 0
| SUB TOTAL |  |  |  |  | 0